## Implementation timetable
Implementation Timetable
Please refer to the sheet Funding windows for details on scheduling of output 2.2
COMPONENTS/OUTPUTS | 2026 |  |  |  | 2027 |  |  |  | 2028 |  |  |  | 2029 |  |  |  | 2030 |  |  |  | 2031 |  |  |  | 2032 |  |  |  | 2031
| Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2
Component 1: Capacity enhanced to achieve climate resilience of housing/community building stock
Output 1.1: Communities, home and business owners and the private sector (including tradespeople, builders and inspectors) are aware of the requirements of the Building Code 2019, as well as the funding opportunity to increase resilience of the building stock
Activity 1.1.1: Awareness raising campaign on Rarotonga and in the Pa Enua, the following actions will be undertaken to ensure that communities, homeowners and trades people are informed and prepared to participate in the project, including the use of gender sensitive language in awareness raising materials and the delivery of gender and SEAH risk trainings at the awareness raising events in both Rarotonga and the Pa Enua under sub-activity 1.1.1.2 | 2026 Q2: Materials delivered
|  | Training 1 | [5 empty] | Training 2 |  |  |  | Training 3
Output 1.2: Facilitation and support of applications for access to the concessional financing from the EDA Facility for climate-resilient housing and community building
Activity 1.2.1: Support and facilitation of applications of quality subproject proposals: Island Councils and Focal Points will actively support the preparation and submission of applications under Windows 1 and 2 of the EDA Facility. This support will include: | bar: 2026 Q3 to 2031 Q4
Component 2 – Operation of the EDA facility to achieve house/building resilience & roll-out of Sub Projects.
Output 2.1: EDA Facility is established with required financial credit worthiness and SP technical review parameters for the management of the Facility, including origination, appraisal, and portfolio management of SPs
Activity 2.1.1: Develop the constitution of the EDA Facility: MFEM will lead the development of the EDA Facility Policy, establishing the legal, governance, and operational framework required for its effective management | 2026 Q1: Draft; 2026 Q2: Adopted by GoCI
Output 2.2: EDA facility management has the technical capacity to effectively manage the EDA Facility and implement the subproject pipeline origination and appraisal and portfolio management | 2026 Q1: See sheet Funding windows for further details of scheduling for output 2.2
Activity 2.2.1: Administration of Subprojects | bar: 2027 Q1 to 2031 Q4
Output 2.3: Construction management and oversight of subprojects implementation will entail completion of 2,205 subprojects with full compliance certification under the 2019 Building Code
Activity 2.3.1: construction management and oversight of SPs | bar: 2027 Q3 to 2031 Q4
Project Monitoring* | 2026 Q1: Establish M&E system; 2026 Q2: Inception Report; 2027 Q1: APR; 2028 Q1: APR; 2029 Q1: APR; 2029 Q3: Interim Evaluation and EDA Facility Evaluation; 2030 Q1: APR; 2031 Q1: APR; 2032 Q1: APR; 2031 Q1: Completion Report; 2031 Q2: Final Evaluation
APR = Annual Performance Report
*In addition to this monitoring requirements, the Funded Activity is also subject to financial reporting per the AMA/FAA, such as Unaudited/Audited Financial Statements, Financial information reports, and other reports as defined in the FAA.